## Dashboard
Agon: The Bible Challenge Roadmap
Visual roadmap generated from GitHub milestones and ROADMAP.md (snapshot 2026-09-29, Agon vNext / ADR-001; includes #522/#523/#524 M0 exit gate).
Near-term path | M0 | M1 | M2 |  | Release gate | 1.0.0 | Parallel tracks | Backlog
Focus | vNext foundation | Five Clues reference | Catalog + migration waves |  | Focus | Local vNext product | Design system, M5/M6 | Candidates, tests
Primary blockers | #509 (#7, #513-#515, #519, #522-#524) | #510 (#402, #4, #516, #522-#524) | #507, #511 |  | Primary blockers | #15 (M0, M1, #353, #357, #7) | #99-#104, #516, #357 | #507 dispositions; #5, #6
Track | Milestone | Issues | Status | Done | M0 | M1 | M2 | M3 | M4 | M5/M6 | 1.0 | M7/M8 | M9/M10 | Dependency note
Testing, Host Mode, Host Remote | 0.1.x-0.3.0 | #1-#3, #8-#10, #94-#96 | Done | ■ | [9 empty] | Shipped. Legacy runtime runs all 32 implemented GameIds.
Agon Brand & Design System | Track | #99-#102, #104, #117, #298 | Parallel now |  | ■ | ■ | [7 empty] | Renderer-agnostic; #117 rename continuity blocks #99. Feeds vNext surfaces.
vNext Architecture Foundation | M0 | #509 + 27 sub-issues, #519, #522, #523, #524 | In progress (#7/#515/#362 done; #314 next) |  | ■ | [8 empty] | Needs ADR-001 (#512, merged). Exit: minimal GameDefinition runs without Electron/renderer/network; legacy games still launch; CI enforces boundaries; AND #522/#523/#524 (gameplay lifecycle, gameplay shell/viewport, cross-game scoring normalization) sufficiently defined/tested for #510 to begin.
vNext Reference Migration | M1 | #510, #402, #4, #516 | Proof gate |  |  | ■ | [7 empty] | Five Clues end-to-end (fallback Name That Book). Needs #509, #402, #4, #516, #522, #523, #524. Proves the M0 exit-gate contracts; does not itself define the cross-game scoring scale.
Catalog & Migration Classification | M2 | #507, #511, #304, #385 | #507 now; #511 after M1 |  | ■ | ■ | ■ | [6 empty] | #511 needs #507 and #510. Output creates M4 wave and M3 capability issues.
Core Capability Extraction | M3 | Cards, randomizers, timer, image board, board play, race, journey, relationships | After M0/M2 |  |  |  |  | ■ | ■ |  |  |  |  | Engines/capabilities on Engine SDK #447; each names its consumers.
Existing Game Migration Waves | M4 | #331 epic, #305-#309, #321 | After #511 | [5 empty] | ■ | ■ | ■ |  |  | Waves by capability family; legacy variants #56-#58, #87 land after their wave.
Renderer / Experience Decomposition | M5 | #103, #105-#108, #316, #369-#372 | Alongside M4 |  |  |  | ■ | ■ | ■ | ■ |  |  |  | Starts after #510/#516; no giant App.tsx rewrite.
Controller & Shared/LAN Contracts | M6 | #11-#20, #50-#51, #109-#113, #357 | Alongside M4 |  |  |  | ■ | ■ | ■ | ■ |  |  |  | Absorbs 0.4.0 Phone Mode Stage 1; controllers use vNext intents, not WebSocket details.
Stabilization (Local vNext product) | 1.0.0 | #15, #115 | Release gate | [7 empty] | ■ |  |  | M0 + M1, design system, local controllers on vNext, save/resume, CI/regression/package green, representative migrated families.
Tournaments & Persistent Events | Track | #21, #189-#198, #310 | After M0 | [5 empty] | ■ | ■ | ■ |  |  | Needs #353 persistence and #364 ledger; #191/#194 additionally need #524/#364 Event-contribution contract; #197 and #310 need M4-migrated games.
Packaging, Distribution & Entitlements | Track | #24, #31-#37, #319, #324, #344-#347, #425-#436 | Reconcile duplicates |  |  |  |  | ■ | ■ | ■ | ■ | ■ |  | Older/newer duplicates must be reconciled first; needs M0 content contract.
Themed Content & Seasonal Packs | Track | #25-#30, #38-#45 | Flexible order |  |  |  |  | ■ | ■ | ■ | ■ | ■ |  | Content-only work is allowed under the legacy freeze; pack model #24 is in Packaging.
New General Agon Catalog on vNext | M7 | Baseball, Blockbusters, Pairs of Faith, Wayfinder, Multitude, ... | After capability + #507 | [8 empty] | ■ | ■ | Never targets the legacy engine; grouping via track:* labels.
Agon Kids on vNext | M8 | #234, #235, #257, #325-#335, #484-#506 | After capability + Kids foundation | [8 empty] | ■ | ■ | Separate AGON_KIDS family; shares infrastructure, never GameDefinitions.
Shared/Hosted Platform | M9 | #359, #360, #377, #378, #382, #383, #411 | After M6 | [9 empty] | ■ | Adapters/services only; Local stays supported.
Legacy Retirement | M10 | #517 | Last | [9 empty] | ■ | Every retained game migrated or superseded; then delete gameEngine.ts path.
Platform Hardening & Operations | Track | #322, #323, #373-#376, #416-#421 | Mostly after M4 | [8 empty] | ■ | ■ | Diagnostics, replay, size budgets, docs publishing, localization.
General + Kids Candidates, Testing | Backlog | #200-#233, #236-#279, #5, #6 | Via #507 disposition | [8 empty] | ■ | ■ | Candidates leave the backlog only through a #507 disposition into M7/M8.
Read this left to right: each step is an intended sequence bucket, not a calendar date. The design system and #507 can run in parallel with M0; M5/M6 start once #510 proves the first vNext surfaces and grow alongside M4. M0 is not complete until #522 (gameplay lifecycle/resolution policies), #523 (gameplay shell/viewport contract) and #524 (cross-game scoring normalization, coordinated with #364) are defined and tested — #510 proves them but does not itself set the cross-game scoring scale. 1.0 is the first release-quality Local vNext product; % of games migrated is tracked as a metric (0 of 32 on 2026-09-29), not a release gate. Native GitHub blockedBy links are the source of truth. Full single ordered sequence (all 444 open issues): see ROADMAP.md's "Full execution order" section.
Track | Open issues
Agon Brand & Design System | 7
vNext Architecture Foundation | 30
vNext Reference Migration | 5
Catalog & Migration Classification | 4
Core Capability Extraction | 65
Existing Game Migration Waves | 12
Renderer / Experience Decomposition | 20
Controller & Shared/LAN Contracts | 31
Stabilization (Local vNext product) | 2
Tournaments & Persistent Events | 11
Packaging, Distribution & Entitlements | 33
Themed Content & Seasonal Packs | 14
New General Agon Catalog on vNext | 70
Agon Kids on vNext | 27
Shared/Hosted Platform | 11
Legacy Retirement | 1
Platform Hardening & Operations | 17
General + Kids Candidates, Testing | 82

## Milestones
Milestone Summary
Open/closed counts and planning notes by GitHub milestone.
Milestone | Issues | Open | Closed | Planning note
0.1.x - Automated Testing Foundations | #1-#3 | 0 | 3 | Done.
0.2.0 - Host Mode / Game Master Controls | #8-#10, #77-#86 | 0 | 11 | Shipped in v0.2.0.
0.3.0 - Host Remote (Phone/Tablet Host Controller) | #94-#96 | 0 | 3 | Shipped in v0.3.0; LAN server reused by M6.
M0 - vNext Architecture Foundation | #509 (+27 sub-issues), #519, #522, #523, #524 | 32 | 0 | Contracts, AgonRuntime, Engine SDK, Offline adapter, LegacyGameAdapter #513, boundary CI #515, plus M0 exit gate #522/#523/#524 (gameplay lifecycle, gameplay shell/viewport, cross-game scoring normalization coordinated with #364) required before #510 begins.
M1 - vNext Reference Migration | #510, #402, #4, #516 | 5 | 0 | Five Clues end-to-end, proving #522/#523/#524; proof gate for bulk migration. Does not itself set the cross-game scoring scale.
M2 - Catalog & Migration Classification | #507, #511, #304, #385 | 4 | 0 | Audience-safe catalog audit + migration waves.
M3 - Core Capability Extraction | 65 issues | 65 | 0 | Reusable engines/capabilities with named consumers.
M4 - Existing Game Migration Waves | #331, #305-#309, #321, ... | 12 | 0 | Waves defined by #511; legacy variants after their wave.
M5 - Renderer / Experience Decomposition | #103, #105-#108, #369-#372, ... | 20 | 0 | Bounded vNext surfaces; shrink App.tsx.
M6 - Controller & Shared/LAN Contract Migration | #11-#20, #50-#51, #109-#113, #357, ... | 31 | 0 | Phone/Host Remote via Controller intents.
M7 - New General Agon Catalog on vNext | 70 issues | 70 | 0 | New AGON_GENERAL games after capability + #507.
M8 - Agon Kids on vNext | 27 issues | 27 | 0 | AGON_KIDS family, Journeys, Activity Events.
M9 - Shared/Hosted Platform Implementations | 11 issues | 11 | 0 | After M6; adapters, not game forks.
M10 - Legacy Retirement | #517 | 1 | 0 | Remove legacy path when unused.
1.0.0 - Stabilization | #15, #115 | 2 | 0 | First release-quality Local vNext product.
Track - Agon Brand & Design System | #99-#102, #104, #117, #298 | 7 | 0 | Parallel now.
Track - Tournaments & Persistent Events | #21, #189-#198, #310 | 11 | 0 | After M0 persistence/ledger; #191/#194 also need #524/#364 Event-contribution contract; #197/#310 need M4.
Track - Packaging, Distribution & Entitlements | 33 issues | 33 | 0 | Reconcile licensing/pack duplicates first.
Track - Themed Content & Seasonal Packs | #25-#30, #38-#45 | 14 | 0 | Content-only; allowed under legacy freeze.
Track - Platform Hardening & Operations | 17 issues | 17 | 0 | Mostly after M4.
Backlog - General Candidates | #200-#233, #289, #291, #310, #474 | 38 | 0 | Exit via #507 disposition into M7.
Backlog - Agon Kids Candidates | #236-#279 | 42 | 0 | Exit via #507 disposition into M8.
Backlog - Remaining Testing | #5, #6 | 2 | 0 | #4 moved to M1, #7 to M0.
Milestone | Open
0.1.x - Automated Testing Foundations | 0
0.2.0 - Host Mode / Game Master Controls | 0
0.3.0 - Host Remote (Phone/Tablet Host Controller) | 0
M0 - vNext Architecture Foundation | 32
M1 - vNext Reference Migration | 5
M2 - Catalog & Migration Classification | 4
M3 - Core Capability Extraction | 65
M4 - Existing Game Migration Waves | 12
M5 - Renderer / Experience Decomposition | 20
M6 - Controller & Shared/LAN Contract Migration | 31
M7 - New General Agon Catalog on vNext | 70
M8 - Agon Kids on vNext | 27
M9 - Shared/Hosted Platform Implementations | 11
M10 - Legacy Retirement | 1
1.0.0 - Stabilization | 2
Track - Agon Brand & Design System | 7
Track - Tournaments & Persistent Events | 11
Track - Packaging, Distribution & Entitlements | 33
Track - Themed Content & Seasonal Packs | 14
Track - Platform Hardening & Operations | 17
Backlog - General Candidates | 38
Backlog - Agon Kids Candidates | 42
Backlog - Remaining Testing | 2

## Issue Map
Issue Relationship Map
Grouped issue references, blockers, and planning action.
Issues | Work item | Milestone | Status | Depends on | Planning action
#512 | ADR-001 + vNext migration spec | Merged | Closed | None | Governing architecture
#509 | vNext foundation epic (27 sub-issues) | M0 | Open | None (root) | Start here
#7, #515 | CI + architecture-boundary / legacy-freeze guard | M0 | Closed | #3; #515 needs #7 | Done
#362 | Canonical domain model, stable IDs, ownership boundaries | M0 | Closed | None | Done
#314, #447-#450 | GameDefinition registry, Engine SDK | M0 | Open | #362 (done) -> #314 -> #447 | Foundation core, next
#350, #448, #351, #353 | Intents/events, projections, session persistence | M0 | Open | #349, #350 | Foundation core
#513, #514, #519 | LegacyGameAdapter, Offline adapter, local security baseline | M0 | Open | #314; #349 | M0 exit items
#522, #523, #524 | Gameplay lifecycle/resolution policies, gameplay shell/viewport contract, cross-game scoring normalization | M0 | Open | #509; #524 coordinates with #364 | M0 exit gate — required before #510 begins; kept as three distinct issues (behavior, layout, scoring)
#510 | Five Clues reference migration | M1 | Open | #509, #402, #4, #516, #522, #523, #524 | Proof gate; proves #522/#523/#524, does not itself define the cross-game scoring scale
#402, #4, #516 | Answer evaluation, oracle tests, vNext surface host | M1 | Open | #350, #338; #314, #351 | M1 prerequisites
#507 | Audience-boundary catalog audit | M2 | Open | None (root) | Parallel now
#511 | Migration-wave classification | M2 | Open | #507, #510 | After M1
#331, #305-#309 | Migration waves epic + wave placeholders | M4 | Open | #511 | Scope from #511
#56-#58, #87 | Legacy variants (timeline, Director's Cut, Word Ladder) | M4 | Open | Owning wave | Do not implement yet
#11-#20, #50-#51 | Phone Mode (folded into M6) | M6 | Open | #510, #350, #351 | Do not implement yet
#103, #105-#108 | Agon UI redesign as vNext surfaces | M5 | Open | #510, #516 | Do not implement yet
#99-#102, #117 | Brand & design system | Track | Open | #117 -> #99 -> #100 -> #101 -> #102 | Parallel now
#15 | 1.0.0 stabilization (Local vNext) | 1.0.0 | Open | #509, #510, #353, #357, #7, #305-#308, UI | Release gate
#189-#198, #310 | Tournaments & persistent events | Track | Open | #314, #353, #364; #191/#194 also need #524; #197/#310 need M4 | After M0; #197/#310 after M4
#130-#169, #280-#285 | Cards, randomizers, timer, image board | M3 | Open | #447, #142, #156 | After M0
M7 games | Pairs of Faith, Wayfinder, Multitude, Baseball, ... | M7 | Open | #509 + capability + #507 | Do not implement yet
M8 games | Kids games, Journeys, Activity Events | M8 | Open | #234 + capability | Do not implement yet
#359, #360, #377, #378 | Shared/Hosted runtimes and Stage adapters | M9 | Open | #357 and M6 contracts | Future
#517 | Legacy retirement epic | M10 | Open | #331 | Last
#23/#286, #243/#484, #304, #321, #363, ... | Duplicate candidates (phase 7) | Various | Open | Requirements migration | Do not close without approval

## Chart Data
Chart Data
Source data used by the roadmap charts.
Order | Milestone | Track | Start step | Duration | Open | Closed | Issues | Theme | Dependency note
1 | 0.1.x-0.3.0 | Testing, Host Mode, Host Remote | 1 | 1 | 0 | 17 | #1-#3, #8-#10, #94-#96 | Legacy baseline | Shipped. Legacy runtime runs all 32 implemented GameIds.
2 | Track | Agon Brand & Design System | 2 | 2 | 7 | 0 | #99-#102, #104, #117, #298 | Design | Renderer-agnostic; #117 rename continuity blocks #99. Feeds vNext surfaces.
3 | M0 | vNext Architecture Foundation | 2 | 1 | 30 | 2 | #509 + 27 sub-issues, #519, #522, #523, #524 | Architecture | Needs ADR-001 (#512, merged). Exit: minimal GameDefinition runs without Electron/renderer/network; legacy games still launch; CI enforces boundaries; AND #522/#523/#524 (gameplay lifecycle, gameplay shell/viewport, cross-game scoring normalization) sufficiently defined/tested for #510 to begin.
4 | M1 | vNext Reference Migration | 3 | 1 | 5 | 0 | #510, #402, #4, #516 | Architecture | Five Clues end-to-end (fallback Name That Book). Needs #509, #402, #4, #516, #522, #523, #524. Proves the M0 exit-gate contracts; does not itself define the cross-game scoring scale.
5 | M2 | Catalog & Migration Classification | 2 | 3 | 4 | 0 | #507, #511, #304, #385 | Planning | #511 needs #507 and #510. Output creates M4 wave and M3 capability issues.
6 | M3 | Core Capability Extraction | 5 | 2 | 65 | 0 | Cards, randomizers, timer, image board, board play, race, journey, relationships | Capabilities | Engines/capabilities on Engine SDK #447; each names its consumers.
7 | M4 | Existing Game Migration Waves | 6 | 3 | 12 | 0 | #331 epic, #305-#309, #321 | Migration | Waves by capability family; legacy variants #56-#58, #87 land after their wave.
8 | M5 | Renderer / Experience Decomposition | 4 | 4 | 20 | 0 | #103, #105-#108, #316, #369-#372 | Experience | Starts after #510/#516; no giant App.tsx rewrite.
9 | M6 | Controller & Shared/LAN Contracts | 4 | 4 | 31 | 0 | #11-#20, #50-#51, #109-#113, #357 | Phones | Absorbs 0.4.0 Phone Mode Stage 1; controllers use vNext intents, not WebSocket details.
10 | 1.0.0 | Stabilization (Local vNext product) | 8 | 1 | 2 | 0 | #15, #115 | Release quality | M0 + M1, design system, local controllers on vNext, save/resume, CI/regression/package green, representative migrated families.
11 | Track | Tournaments & Persistent Events | 6 | 3 | 11 | 0 | #21, #189-#198, #310 | Game modes | Needs #353 persistence and #364 ledger; #191/#194 additionally need #524/#364 Event-contribution contract; #197 and #310 need M4-migrated games.
12 | Track | Packaging, Distribution & Entitlements | 5 | 5 | 33 | 0 | #24, #31-#37, #319, #324, #344-#347, #425-#436 | Distribution | Older/newer duplicates must be reconciled first; needs M0 content contract.
13 | Track | Themed Content & Seasonal Packs | 5 | 5 | 14 | 0 | #25-#30, #38-#45 | Content | Content-only work is allowed under the legacy freeze; pack model #24 is in Packaging.
14 | M7 | New General Agon Catalog on vNext | 9 | 2 | 70 | 0 | Baseball, Blockbusters, Pairs of Faith, Wayfinder, Multitude, ... | Games | Never targets the legacy engine; grouping via track:* labels.
15 | M8 | Agon Kids on vNext | 9 | 2 | 27 | 0 | #234, #235, #257, #325-#335, #484-#506 | Kids | Separate AGON_KIDS family; shares infrastructure, never GameDefinitions.
16 | M9 | Shared/Hosted Platform | 10 | 1 | 11 | 0 | #359, #360, #377, #378, #382, #383, #411 | Platform | Adapters/services only; Local stays supported.
17 | M10 | Legacy Retirement | 10 | 1 | 1 | 0 | #517 | Architecture | Every retained game migrated or superseded; then delete gameEngine.ts path.
18 | Track | Platform Hardening & Operations | 9 | 2 | 17 | 0 | #322, #323, #373-#376, #416-#421 | Operations | Diagnostics, replay, size budgets, docs publishing, localization.
19 | Backlog | General + Kids Candidates, Testing | 9 | 2 | 82 | 0 | #200-#233, #236-#279, #5, #6 | Backlog | Candidates leave the backlog only through a #507 disposition into M7/M8.